Implementation Plan RE Curriculum 2025/2026

EYFS / Year 1 class and Year 1 / 2 class will use ‘Lighting the Path-Source to Summit’ resources from September 2025

LKS2 classes will use the Come and See resources from September 2025 and will use the diocesan resources from January 2026 until ‘Lighting the Path-Source to Summit’ becomes available in September 2026

| Date | Action | Responsibility |
| --- | --- | --- |
| June- July 2025 | Staff training Lighting the Path • Zoom training for EYFS, Year 1 and Year 2 by Diocese | HT |
| June- July 2025 | Download Diocesan resources and prepare transition plan • Resources saved to T:Drive • Inset Day training plan agreed | HT/DHT |
| June- July 2025 | Order Lighting the Path Resources for EYFS & KS1 | Office Manager |
| July 2025 | EYFS & KS1 Teachers familiarise themselves with Lighting the Path resources, activities and assessment. First 2 branches- Creation to Covenant and Prophesy and promise | RE Lead |
| September 2025 | Inset training - EYFS / KS1 Lighting the path - KS2 Diocesan resources - Assessment- introduction of cold and hot tasks - Knowledge nuggets - WAGOLLs | RE leaders D McBride ( External) |
| September-October 2025 | - Lesson drop in’s to monitor quality first teaching and provide coaching support - Staff knowledge and confidence survey | HT/ DHT |
| October 2025 | First review meeting to gather teacher feedback on ‘Lighting the Path’ and diocesan resources implementation RE Lead / Head teacher • Book Look- English book comparison • Identify training needs • Resource requirements | SLT/ RE team |
| November 2025 | Catholic School Cluster meeting to review ‘Lighting the Path’ and moderate books | RE leader |
| November 2025 | Diocesan Cluster zoom feedback • Zoom dates TBC by Diocese | RE leader |
| December 2025 | Receipt of next 2 branches of EYFS / KS1 Lighting the Path – Galilee to Jerusalem and Desert to Garden • Staff familiarisation and planning Moderation and Assessment data review at pupil progress meetings | RE leader |
| December 2025 | Mid-year evaluation of Lighting the Path usage and impact in EYFS & KS1 and Diocesan resources in KS2 | RE Team |
| January – March 2026 | Begin planning for phased rollout of Lighting the Path Resources to KS2- Diocesan timescales TBC • Purchase KS2 resources | RE leader Office manager |
| March 2026 | Moderation and Assessment data review at pupil progress meetings | HT/DHT |
| March 2026 | Review meeting to gather teacher feedback on ‘Lighting the Path’ and diocesan resources implementation • Book Look- English book comparison • Identify training needs • Resource requirements | RE leader |
| March 2026 | Catholic School Cluster meeting to review ‘Lighting the Path’ and moderate books | RE leader |
| March 2026 | Receipt of next 2 branches of EYFS / KS1 Lighting the Path – To the ends of the Earth and Dialogue & Encounter • Staff familiarisation and planning | RE leader |
| March 2026 | Diocesan Cluster zoom feedback • Zoom dates TBC by Diocese | RE leader |
| June 2026 | Full review of Lighting the Path and training for KS2 • KS2 Zoom training by diocese TBC | RE leader |
| July 2026 | KS2 Teachers familiarise themselves with Lighting the Path resources, activities and assessment. First 2 branches- Creation to Covenant and Prophesy and promise | RE leader |